## Sheet1
Requirement ID | Requirement Description | Design Reference | Implementation Module | Test Case ID | Status
RQ-01 | User login with role-based access control | UI-D-01, Auth-D-01 | Login Module, Role Manager | TC-01 to TC-03 | ✅ Verified
RQ-02 | Lecturer can mark attendance in real-time | ATT-D-01 | Attendance Module | TC-04 to TC-06 | ✅ Verified
RQ-03 | System supports GPS location tracking during attendance | ATT-D-02, GPS-D-01 | Location Tracker | TC-07 | ✅ Verified
RQ-04 | Student photo capture for ID verification | PHOTO-D-01 | Camera Integration | TC-08 | ✅ Verified
RQ-05 | Device registration and verification | DEVICE-D-01 | Device Manager | TC-09 to TC-10 | ✅ Verified
RQ-06 | Students can enroll in courses | COURSE-D-01 | Enrollment Module | TC-11 to TC-12 | ✅ Verified
RQ-07 | Generate downloadable reports (PDF/CSV) by lecturer and admin | REPORT-D-01 | Report Generator | TC-13 to TC-14 | ✅ Verified
RQ-08 | Role-based dashboard for Lecturer, Student, and Admin | UI-D-02 | Dashboard Module | TC-15 to TC-16 | ✅ Verified
RQ-09 | Offline attendance support with local storage and sync on reconnect | SYNC-D-01 | Sync Manager | TC-17 | 🔄 In Progress
RQ-10 | Admin can perform full CRUD on users and courses | ADMIN-D-01 | Admin Control Panel | TC-18 to TC-20 | ✅ Verified
RQ-11 | REST API backend with cloud data storage | API-D-01, CLOUD-D-01 | Backend Server, Database Layer | TC-21 to TC-23 | ✅ Verified
RQ-12 | Secure login with OTP/device/email confirmation for critical actions | AUTH-D-02 | Security Manager | TC-24 to TC-25 | 🔄 In Progress